### Independent Project:

### Project Management Assignment

- To learn how to organize and execute a research project.

- To learn to identify and avoid potential pitfalls.

- To learn to create a realistic research schedule and stick to it.

ASSIGNMENTS

Oct. 10th  & 11th PLANNING

Statement of Work

Define Participants

Oct. 24th & 25th  ORGANIZING

Work Breakdown Schedule

graphical timeline

control questions

Nov. 20th  REVIEW AND REVISE

Dec 3rd Title, Authors, Abstract due by email at noon

Dec 5th POSTER PRESENTATION

present your poster

visit other posters (3 evaluations)

Dec 5th ASSESSMENT

Background:

Project Management, a concept long familiar to the business work, has a place in scientific research as well. Although many scientists dismiss the strategies of project management as irrelevant to the scientific process, and even view it as antithetical to creativity, these strategies can help to reduce wasted work effort, help to track progress (identify lack of it), and help research teams respond quickly to deviations from important aims.

All grant proposal’s include a description of the methods to be used, and a projected timeline for project accomplishment. While a grant proposal may mention potential pitfalls, and alternate strategies, the goal of a grant proposal is to create the APPEARANCE of a streamlined feasible project.

Project Management is NOT the same text that you would write in a grant application to secure funding. The probability of success for a research program is proportional to the amount of thought that has gone into it. The goal of a project management plan is to create a streamlined feasible project (not just the appearance of one).

A Project Management Plan includes

- a description of the methods to be used,

- the qualifications of the researchers involved,

- a timeline for project accomplishment.

- EMPHASIS on potential pitfalls so that they can be avoided.

Once you have decided on a project and decided that is feasible, there are three basic steps to project management.

1-planning

2-orgainization

3-controlling

- Planning:

  - Develop a “statement of work” (see example handout)

    - Purpose

        - Background

          - scientific (include 2-3 key references)

          - personal

        - Scope (bullet points of specific areas of inquiry)

        - Strategy (what type of work will be done)

    - Objectives

        - Statement (desired outcome)

        - Measures (how will success be assessed)

        - Specifications (values to be met for each measure)

    - Constraints

        - Limitations set by others

        - Needs set by the project team

    - Assumptions

        - Statements about uncertain information (risks)

  - Define the participants

    - Drivers – (others with outside influence on your project)

    - Supporters – (people who will perform the work)

    - Observers – (people who have an interest but little influence)

- Organizing:

  - Develop a work breakdown structure (WBS) –A hierarchical outline of all of the work that will have to be performed in your project.  A WBS starts with broad activities and breaks these down into discrete tasks. A WBS is not as detailed as a daily “todo” list. (see example handout)

  - Schedule the project –

    - Event Schedule

        - Target dates

    - Activity Plan

        - Start dates

        - Stop dates

    - Gantt chart:

        - Graphical timeline

  - Assign tasks – Linear chart assigning a series of related tasks to individuals (this looks like a “todo list” for each individual”)

  - Identify communication structure – this is more important with a larger project and more people involved.

- Controlling:

  - Monitor – strategically acquire necessary information

  - Review – evaluate progress relative to plan

  - Revise – adjust dates, responsibilities, etc as needed

  - Communicate and manage risk. – “what ifs”

ASSIGNMENTS

PLANNING Due before Fall break:

Statement of Work (1.a.) 1-2 pages

- Include section 1.a.i – 1.a.iv described above. (use Statement_of_Work_Template.doc available on courses server under lab indy projects)

This outline is prepared before the project is begun.

It defines what the project may involve

It identifies areas that will have to be

Define the Participants (1.b.) 0.5 page

- Name & 1 sentence description for the role of each driver, supporter, and observer.

ORGANIZING due the week after Fall Break:

Work Break Down Schedule (2.a.)

- 1 page hierarchical outline of all work that will be included in this research project

Schedule the project (2.b.)

- A graphical timeline to schedule your project. (user gantt_chart_template.ppt as template, it is on courses server in syllabus under lab indy projects).

Answer the following questions with 1-3 sentences each.

- Where do you anticipate potential shifts in the plan?

- What are the weak points of the plan that might require special attention?

- What are the checkpoints that will indicate the need for a new strategy?

- What can be done to monitor this project?

CONTROLLING due before Thanksgiving break:

Review and Revise -

How has the strategy changed?

Are there new experiments planned?

Have experiments been eliminated from the plan?

Are the drivers and supporters fulfilling duties?

Reschedule the project if necessary (2.b.)

- A graphical timeline to schedule your project. (gantt_chart.xls as template).

(if nothing has changed, turn in the original timeline again stating "on schedule").

POSTER PRESENTATION DECEMBER 5th 1:00 – 4:00 2 hours required

(actual time to be discussed in class)

ASSESSMENT due at the Poster Session or by email: Assess your success (< 1 page)

Did you anticipate all potential shifts in the plan? _________________

- If not, explain the most significant change in plans after project initiation.

Were all of the project goals met? ____________________________

- If not, explain why the goals were not met and identify steps in the process that might have assisted in achieving these goals.

Did the group work together as a team?________________________

- Describe the contributions of each collaborator.

What did you learn from the data you collected?

What did you learn from the research experience?

How would structure independent projects differently?